## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Current sprint | Current sprint | US-TEST-01 | As an admin, I want to authenticate and manage user access so that access is role-appropriate. | Must Have | Authentication / role setup | Nuseba | Tested
Current sprint | Current sprint | US-TEST-02 | As a manager, I want to review employee workload, project skill fit, capacity headroom, performance snapshots, and check-in prompts. | Must Have | Employee profiles and project data | Nuseba | Tested — sample cases
Current sprint | Current sprint | US-TEST-03 | As a manager, I want staffing recommendations to obey explicit availability and overload constraints. | Must Have | Talent Scout and Capacity Balancer | Nuseba | Issue found — investigate
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-TEST-01 | T-TEST-01 | Verify setup status and admin login | 2026-10-14 | 2026-10-14 | Nuseba | Manual testing | Done | 1
US-TEST-01 | T-TEST-02 | Verify invalid-password rejection, employee login, and role-based user-list access | 2026-10-14 | 2026-10-14 | Nuseba | Manual testing | Done / status evidence partial | 2
US-TEST-02 | T-TEST-03 | Test employee review for within-capacity Vance Sterling and Project Aegis | 2026-10-14 | 2026-10-14 | Nuseba | Manual testing | Done | 1
US-TEST-02 | T-TEST-04 | Test employee review for over-capacity Dr. Elena Rostova and Project Aegis | 2026-10-14 | 2026-10-14 | Nuseba | Manual testing | Done | 1
US-TEST-03 | T-TEST-05 | Test staffing recommendations against >=20% availability constraint | 2026-10-14 | 2026-10-14 | Nuseba | Manual testing | Blocked / defect recorded | 1
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | 2026-10-14 | Staffing recommendation results included candidates below the stated 20% availability minimum. | Recorded the finding in the defect tracker; inspect constraint parsing/filtering before more API-backed tests.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-10-14 | 2026-10-14 | Nuseba | Capture expected vs actual results and test both normal and edge cases. | Avoid repeated recommendation requests until API usage is understood. | Continue one test at a time and keep evidence from UI results. | Investigate staffing constraint defect; verify implementation before claiming fix.
2
3
4
5
6
7