## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Nuseba | 2026-10-14 | Staffing Recommendations returns employees who violate the prompt's explicit minimum availability constraint. Prompt required >=20% available capacity and excluded overloaded employees, but results included Vance Sterling (15% available) and Lucas Drake (0% available). Tariq Mansoor (40%) and Devon Ward (50%) also appeared. | Testing / current sprint | Unassigned | Logical | Not fixed. Record for investigation: inspect recommendation filtering and capacity-balancer flow; confirm whether prompt constraints are parsed and enforced as hard filters. | 2026-10-14 | Open | Observed in manual test. Activity log showed 'Workload Constraint Verification' and 'Rebalancing applied' despite non-compliant candidates in final list. Reproduce after reviewing implementation; do not assume external API is the cause.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others