## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Nuseba | 2026-09-03 | AI agent initially responded to unrelated/non-customer-support queries instead of restricting the response to the supported customer-service scope. | Sprint 1 | Nuseba | Logical | Refined the system prompt to restrict the agent to customer-support-related queries and tested it with unrelated inputs. | 2026-09-03 | Closed | Fixed and verified through manual testing.
2 | Nuseba | 2026-09-12 | Employee information could not be retrieved correctly after changing the employee data source from the external service to the SQLite database. | Sprint 2 | Nuseba | Logical | Updated the employee information tool to retrieve records from the SQLite database and tested employee IDs. | 2026-09-12 | Closed | Fixed and verified with employee records.
3 | Nuseba | 2026-09-13 | Some unrelated queries were being routed to the HR Assistant instead of being rejected. | Sprint 2 | Nuseba | Logical | Updated the Coordinator Agent classification to include an IRRELEVANT category and restricted unsupported queries. | 2026-09-13 | Closed | Verified using unrelated queries.
4 | Nuseba | 2026-09-14 | Employee-facing interface required improvement to provide a professional enterprise HR experience. | Sprint 2 | Nuseba | User Interface | Redesigned the interface and integrated the WorkSphere employee-facing web interface. | 2026-09-15 | Closed | Updated and tested the interface.
5 | Nuseba | 2026-09-16 | AI-generated HR responses were affected by temporary API quota/model availability errors during testing. | Sprint 2 | Nuseba | Logical | Retested the application after API availability was restored and verified employee database retrieval independently. | 2026-09-17 | Closed | External service limitation; application functionality verified.
6 | Nuseba | 2026-10-04 | Employee ID extraction incorrectly interpreted the year from a leave date such as 2026-10-10 as the employee ID. | Sprint 3 | Nuseba | Logical | Updated employee ID extraction to ignore YYYY-MM-DD date patterns before extracting employee IDs. | 2026-10-04 | Closed | Fixed and verified with leave-request testing.
7 | Nuseba | 2026-10-04 | Employee, leave and policy requests were not always routed to the correct specialized agent when using the same coordinator flow. | Sprint 3 | Nuseba | Logical | Refined local routing rules in the Coordinator Agent for employee information, leave requests and policy queries. | 2026-10-04 | Closed | Verified using employee, leave and WFH queries.
8 | Nuseba | 2026-10-04 | Duplicate leave requests could be submitted for the same date without checking for an existing request. | Sprint 3 | Nuseba | Logical | Added overlapping leave-request validation before creating a new leave request. | 2026-10-04 | Closed | Verified by submitting the same leave date twice.